## Progress
PUBLIC SERVICE AGREEMENT 2010-2014 (CROKE PARK AGREEMENT)
PART A - PROGRESS ON DEPARTMENTAL /AGENCY ACTION PLAN
For submission by 3 May 2011
1. Better human resource management: Actions to include under this heading include reductions in numbers, redeployment, reconfiguration of service delivery,
revisions in attendance arrangements, better attendance and absence management etc.
Terms of Agreement
2010-2014 |  | Target Date as per |  |  |  |  | Action* | Comment**
(refer to all relevant |  | Current Action Plan
paragraphs)
Introduce Min 5hrs and Max 9 hrs daily into the flexible working time policy based on current office opening hours of 7.30 am to 7.00 pm.
1.8, 4.1, 4.4 CPA |  | Q1 | 2 | 0 | 1 | 1 |  | Policy now introduced which will result in productivity gains for the organisation
2.1 DETI Plan
Introduce revised attendance management policy involving • Currently all sick leave in excess of 2 days must be certified by a Doctor. The Board will now also introduce self certification by staff members for sick leave not certified by a doctor, which is sick leave of less than 2 days duration. • back to work reviews with staff following periods of sick leave
|  | Q1 | 2 | 0 | 1 | 1
1.8, 4.1, 4.4 CPA | [7 empty] | Policy drafted and being finalised for implementation in May 2011. Minor delay due to awaiting outcome of external HR audit which included a review of the sick leave policy. Whilst sick leave has not been an issue for the Board, this updated policy will result in better management of resources and attendance.
2.1 DETI Plan
2. Better Business processes: Actions under this heading would include efficiency measures and improvements to the processes by which your Department/Body
delivers its services to the public, including changes to the technology used, better data management, including around identity, and so on.
Terms of Agreement
2010-2014 |  | Target Date as per |  |  |  |  | Action* | Comment**
(refer to all relevant |  | Current Action Plan
paragraphs)
4.13 | CPA | Q4 | 2 | 0 | 1 | 1 | Optimise benefits of extension of electronic correspondence with stakeholders | For a defined category of cases, formal notifications are now being issued online rather than via Registered post which has resulted in savings in Q1 2011 of €23000. However, these are not savings to the Exchequer but savings to the running costs of the Board, which is self funded through levying a fee on those who use the services.
and annually thereafter
3.1 | DETI Plan
4.13, 4.16 CPA |  | Q4 | 2 | 0 | 1 | 1 | EFT roll–out to medical and other specialist professions. Replace majority of 5,500 cheques currently issued each year
and annually thereafter
2.6, 3.13 DETI Plan
4.13 CPA |  | Q4 | 2 | 0 | 1 | 1 | Implement improvements to on-line application process
|  | Q1 to Q4 20110 |  |  |  |  | Energy saving – in line with the National Energy Efficiency Action Plan 2009-2020 InjuriesBoard.ie will seek to be more energy efficient as well as reducing our energy costs. Actions are to engage with SEAI (Sustainable Energy Authority of Ireland) and implement recommendations. | Report from SEAI has been completed and recommendations are currently being reviewed.
3. Delivering for the Citizen: Actions under this heading would include efficiency measures and improvements to the processes by which your Department/Body
its services to the public, including changes to the technology used, better data management, including around identity, and so on.
Terms of Agreement
2010-2014 |  | Target Date as per |  |  |  |  | Action* | Comment**
(refer to all relevant |  | Current Action Plan
paragraphs)
|  | Q4 | 2 | 0 | 1 | 1 | Reduction in Respondent and Claimant Fees | Fees reduced from February 2011 by €200 per Respondent fee and €5 per Claimant fee. Due to the nature of the claims process the savings do not accrue until 90 days post implementation of the fee reduction. Significant processing cost reductions will be delivered by end of Quarter 2
and annually thereafter

## Sustainable Savings
PUBLIC SERVICE AGREEMENT 2010-2014 (CROKE PARK AGREEMENT)
PART B - SAVINGS VERIFICATION
For submission by 3 May 2011
1. Better human resource management: Actions to include under this heading include reductions in numbers, redeployment, reconfiguration of service delivery, revisions in
attendance arrangements, better attendance and absence management etc.
Terms of Agreement |  |  | Description of the Benefits Achieved: this should include, where possible, a
2010-2014 | Action Implemented | Specific | qualitative description including (i) Reduction in numbers (WTE) employed on activity
(refer to all relevant |  | Target | (ii) Paybill savings (iii) Non-Pay Savings and/or (iv) Actual Costs Avoided
paragraphs) |  | Date
1.3 | Total Reduction in Employee Numbers* | Achieved to | Numbers as at Q1 2010….
|  | end Q1 2011 | Numbers as at Q1 2011….
N/A - not funded by Exchequer. Totally self funded by levying fees on Users of the Service.
2. Better Business processes: Actions under this heading would include efficiency measures and improvements to the processes by which your Department/Body deliver
its services to the public, including changes to the technology used, better data management, including around identity, and so on.
Terms of Agreement |  |  | Description of the Benefits Achieved: this should include, where possible, a
2010-2014 | Action Implemented | Specific | qualitative description including (i) Reduction in numbers (WTE) employed on activity
(refer to all relevant |  | Target | (ii) Paybill savings (iii) Non-Pay Savings and/or (iv) Actual Costs Avoided
paragraphs) |  | Date
3. Delivering for the Citizen: Actions under this heading would include efficiency measures and improvements to the processes by which your Department/Body delivers
its services to the public, including changes to the technology used, better data management, including around identity, and so on.
Terms of Agreement |  |  | Description of the Benefits Achieved: this should include, where possible, a
2010-2014 | Action Implemented | Specific | qualitative description including (i) Reduction in numbers (WTE) employed on activity
(refer to all relevant |  | Target | (ii) Paybill savings (iii) Non-Pay Savings and/or (iv) Actual Costs Avoided
paragraphs) |  | Date